## Sheet1
ACTIONS REQUIRED – SCHOOL BUILDING EXTERNAL
Last Updated 18/11/24
No | Action Required | Location | Logged | By Whom | Notes | Deadline | Status | Date Complete
1 | Wooden fascia boards around the school need repairing/repainting. | External | Not Known | FK | Boards peeling, need to be sanded back and repainted. | 2024-09-01 | Complete | Summer 24
2 | Front of school fascia boards completed Summer 2022. | External | Not Known | FK | Boards peeling, need to be sanded back and repainted. | 2024-09-01 | Complete | Summer 24
3 | Repoint outside wall of Yr 3 classroom on the corner near the PE shed. | External | Not Known | FK | Potential for water ingress to Y3 Classroom | 2024-05-01 | Complete | Summer 24
4 | Replace hard flooring in Yr R, 1, 2, admin corridor to staff room door. | Internal | Not Known | External Contractor | FK sourced quotation from SCG Flooring Ltd for £7,862 - £8,829 + VAT | NA | On Hold | NA
6 | Floor uneven between admin corridor and corridor to staff room/PPA room. To be repaired during flooring replacement above. | Internal | Not Known | External Contractor | On Hold | NA | On Hold | NA
7 | Replace hard flooring in Yrs 3, 4, 5. | Internal | Not Known | External Contractor | FK sourced quotation from SCG Flooring Ltd for £9,835 - £11,058 + VAT | NA | On Hold | NA
8 | Replace carpets in Yrs 1, 2, 3, 4, and 5. | Internal | Not Known | External Contractor | FK sourced quotation (Feb 2024) from KH Flooring Specialists for £8,282 + VAT | NA | On Hold | NA
9 | Replace foyer carpet. | Internal | Not Known | External Contractor |  | NA | On Hold | NA
10 | Ceilings in library, HE room, resources area, upper school corridor looking tatty and will eventually need replacing. | Internal | Not Known | External Contractor |  | NA | On Hold | NA
11 | Replace brown carpet in KS2 corridor and resources corridor. | Internal | Not Known | External Contractor |  | NA | On Hold | NA
12 | Paint hall skirting boards | Internal | Not Known | FK |  | Summer 2024 | Complete | Summer 24
13 | Clean hall curtains | Internal | Not Known | FK to investigate |  | Summer 2024 | Complete | Summer 24
14 | Paint school kitchen changing room and toilet area | Internal | Not Known | FK |  | 2024-02-01 | Complete | Move to Summer 2024
15 | Paint Ark kitchen – Walls, skirting and door frame | Internal | Not Known | FK |  | 2024-04-01 | Not Started | Move to Summer 2024
16 | Paint School Office | Internal | Not Known | FK |  | 2024-02-01 | Complete | 2024-02-01
17 | Clean Year R Art Room windows | Internal | Not Known | FK |  | 2024-02-01 | Complete | 2024-02-01
18 | Paint Year R Art Room | Internal | Not Known | FK |  | 2024-02-01 | Complete | 2024-02-01
19 | Paint Year 1 doorframe to teachers’ cupboard | Internal | Not Known | FK |  | 2024-04-01 | Not Started | Move to Summer 2024
20 | Paint Year 1 toilet area | Internal | Not Known | FK |  | 2024-02-01 | Complete | 2024-04-01
21 | Paint KS2 corridor walls | Internal | Not Known | FK |  | 2024-02-01 | Not Started | Move to Summer 2024
22 | Paint KS2 boy’s toilet | Internal | Not Known | FK |  | 2024-02-01 | Complete | 2024-02-01
23 | Paint ceiling wells in KS2 corridor and all KS2 classrooms | Internal | Not Known | FK |  | 2024-04-01 | Not Started | Move to Summer 2024
24 | Clean ceiling well panel/tiles in Years R to 2. | Internal | Not Known | FK |  | 2024-04-01 | Not Started | 2024-04-01
25 | Paint Year 4 classroom walls | Internal | Not Known | FK |  | 2024-04-01 | Not Started | Move to Summer 2024
26 | Replace broken plug socket in Year 4 classroom. | Internal | Not Known | FK discuss with electrician |  | 2024-04-01 | Complete | 2024-04-01
27 | Paint Year 5 door frame | Internal | Not Known | FK |  | 2024-04-01 | Not Started | Move to Summer 2024
28 | Wash Year 6 radiator | Internal | Not Known | FK |  | Summer 2024 | Complete | Move to Summer 2024
29 | Replace screw missing from Year 2 whiteboard | Internal | Not Known | FK |  | Summer 2024 | Complete | Summer 2024
30 | Replace broken extractor fan in disabled/visitor toilet. | Internal | Not Known | FK discuss with electrician |  | Summer 2024 | Complete | Summer 2024
31 | Replace door handle on SBM cupboard | Internal | Not Known | FK |  | Summer 2024 | Complete
32 | Staff car park surface eroding needs resurfacing. | Grounds | Not Known | FK to investigate how to repair | DWC/FK obtained quotes in 2022, circa £20K | na | On Hold | NA
33 | Concrete area adjoining upper playground and quiet area broken and raised. | Grounds | Not Known |  | Damage caused by roots under the tarmac. Unless the area represents a trip hazard, proposed to put on hold | Summer 2024 | On Hold | na
34 | EYFS canopy is dirty and needs cleaning. | Grounds | Not Known | Aura (installers) | WC obtained quote from Aura £995. IW decided not to proceed. | 2024-04-01 | On Hold | na
35 | EYFS area flooring lifting slightly under canopy. | Grounds | Not Known | FK to investigate how to repair |  | 2024-04-01 | Not Started
36 | Wooden edging between upper playground and boundary to be replaced. | Grounds | Not Known | FK |  | 2024-02-01 | Complete
37 | Cut back tree above PE shed and EYFS canopy | Grounds | Not Known | FK |  | 2024-02-01 | Complete | Summer 2024
38 | Fix broken slat on Wildlife Area bridge. | Grounds | Not Known | FK | trip hazard. | Summer 2024 | Complete | Summer 2024
39 | Replace missing gutter hook on PE shed near EYFS canopy. | Grounds | Not Known | FK |  | Summer 2024 | Complete | Summer 2024
40 | Cement at sides of roof (under roof tiles) cracked and breaking away. Concerns that water may enter and cause a leak. | Bungalow | Not Known | FK | FK to investigate how to repair | 2025-01-31 | Not Started
41 | Lots of moss built up on roof tiles. | Bungalow | Not Known | FK | FK to investigate how to repair | 2025-01-31 | Not Started
42 | Soffitt at front of building is flaking, needs to be rubbed down and pinted | External | 2024-11-18 | FK | Needs to be done in drier weather | 2025-09-01 | Not Started
43 | "Keep Clear" sign on playground vehiclular access gate is illegible | External | 2024-11-18 | FK | Sign needs to be ordered | 2024-12-20 | Not Started
44 | Kitchen Delivery Door rotten at base. Frame needs filling and painting | External | 2024-11-18 | FK | potential to let in water or pest. Gaps are sizeable. Frame will need to be replaced. |  | Not Started
45 | Boiler vent at side of boiler room is corroded and damaged - needs replacing | External | 2024-11-18 | Plumber | Potential for condensation to back up into the brickwork |  | Not Started
46 | Coloured panels on side of school (Facing Trinity farm)need to be washed down | External | 2024-11-18 | FK | Algae build up, unsightly |  | Not Started
47 | Algae build up on quiet area paving , needs to be jetwashed | External | 2024-11-18 | FK | Potential slip hazard during wet weather |  | Not Started
48 | Sports shed roof leaking - needs to be reaplced | External | 2024-11-18 | FK | Potential for water damage to contents. Longer term the structure of the building may be affected |  | Not Started
49 | Algae build up in EY area - needs to be jetwashed | External | 2024-11-18 | FK | Potential slip hazard during wet weather |  | Not Started
50 | Litter bin in EY area is broken and needs to be replaced | External | 2024-11-18 | FK | Bin is damaged, plastic is broken |  | Not Started
51 | Wall by salt shed needs to be reponted - damp extending through to Admin Coridor | External | 2024-11-18 | FK | Water is penetrating the interior wall 8" above floor level\DPC |  | Not Started
52 | Deputy head's office ceiling needs to be repainted | Internal | 2024-11-18 | FK | Tiles will need to be replaced eventually but could be refreshed with a coat of paint |  | Not Started
53 | Carpet in Y3 starting to lift needs to be replaced. | Internal | 2024-11-18 | carpet fitter | Carpet is lifting at the corners, has been re-stuck multiple times |  | Not Started
54 | Lino in Y6 peeling and needs to be replaced | Internal | 2024-11-18 | carpet fitter | Quote received from Thames flooring for £1,992 for replacement. Potential trip hazard if left as is. |  | Not Started
55 | Library doors are peeling and need to be repainted | Internal | 2024-11-18 | FK | Doors painted recently but not work completed poory. Needs to be re-done |  | Not Started
56 | Kitchen area - Walls & ceiling need to be painted | Internal | 2024-11-18 | FK | kitchen area is scruffy and in need of painting |  | Not Started
57 | Door frame in Y2 courtyard is rotten needs to be replaced | Internal | 2024-11-18 | FK | Frame has rotted away completely at ground level, will need to be replaced. |  | Not Started
58 | Mastic needs to be replaced around Y2 Sinks | Internal | 2024-11-18 | FK | gap around back of sink adjoining the tiled splashback |  | Not Started
59 | Twelve15 Kitchen corridor doors need to be repainted (x8) | Internal | 2024-11-18 | FK | All doors have had stickers applied and are scratched. |  | Not Started
60 | Kitchen corridor ceiling tiles need to be painted | Internal | 2024-11-18 | FK | very scruffy, will need to be replaced at some point but for now would benefit from a coart of paint |  | Not Started
61 | Grid in playground need to be unblocked | Grounds | 2024-11-18 | FK | playground filling with water during times of heavy rain | 2024-11-16 | Not Started
62 | Repair Fire Exit door in Y3 | Internal | 2024-08-01 | External Contractor | Requires new door | 2024-09-01 | Complete | 2024-08-24
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84